## Sheet1
Platform | Work Completed: 14/01/2020 | Android User: Work to be deliver 31/01/2020 | Android User: Pending/Work Done | User: Pending Work
Android User | Splash Screen |  | 1. Offers/Promotional cards: *API Done *Admin panel needed for this Offers/Promotional cards functionality to add different offers related to services. (Pending) *Partial functionality is done by developer side. | 1. Offers/Promotional cards & Profile Offers tab functions: : *Screen needed & admin panel needed for this functionality Resource Name: Aman & Aayushi
| Walkthrough Screen | 2. Whole functionality Notification Integration: * User side: Service book notification: Done *User side: Service accepted by professional: Done *User side: Service started by professional: Done *User side: Service ended by professional: Done *User side: Service start OTP (push notification): Done *User side: Service end OTP (push notification): Done | 2. Add Promo Code (Promotion): *API Done *Admin panel needed for this Add Promo Code functionality. (Pending) *Partial functionality is done by developer side. | 2. Payment gateway: Production level pending *We need client account details for verification.
| Sign Up | 3. Payment gateway: *PayPal---Integrated & done for testing purpose. *Card Number: 601100099130009 *Expiry Date: 12/2023 *CVV: 123 | 3. Payment gateway: *PayPal--Production level pending *We need client account details for verification. | 3. Profile: Rate: * Implemented after Live application.
| Login |  | 4. Whole functionality Notification Integration: *User side: Service rejected by professional (after accepting leads): Pending | 4. Cancellaton of Service - There will be fees for cancelation which will escalate based on what phase of dispatch we are. For any basic cancellation (jobs under 200$) we can have a fee of say 25$. for larger sales, we will charge a percentage which is graded based on how close our tradesmen are to arriving at the project. If cancelled after tradesmen have been dispatched, we may charge say 25% of whatever the total sale was. For big jobs cancelled before mobilization, we will charge 5 or 10%
| Forget Password |  | 5. Profile: Offers tab functions: *Pending *Note: This point is related to point number 1. | 5. Client pay structure: It depends on Admin panel of mein haus, 20% flat for every service goes to owner of the mein haus after billing, other rest 80 % payment paid to pro. Resource Name: Aayushi
| Home page: Different listed services, Services details, Search services, Popular services |  | 6. Profile: About Mein Haus: *Contact Details needed by Client | 6. User side: Some Cases
| Services page: Different listed services, Search services, Services details |  | 7. Profile: Rate: * Implemented after Live application.
| Service bookings |  | 8. User side: Some Cases: *bookings, services etc…Pending
| Booking Details Page: Upcoming & Past bookings on the basis of booking status |  | 9. User Terms & Conditions: *Needed according to client
| Add promo code: Partial done |  | 10. User Ratings (for professional): *API Needed ----Done *Screen needs to design ------Done *Notification needed (for users to rate professionals)
| Choose Professional |  | 11. Include services: *Civil work-----Done for Area wise one service i.e Flooring & Tile is implemneted *Areawise and contract wise pricing will be done(per square foot) and for entering area, field is to be added at user side at the time of booking areawise services.......Done for one service only i.e. Flooring & Tile
| Professional details |  | 12. Taking disclaimer and budgeting from customer: *Needs to discussed.
| Booking cancel |  | 13. Agreement policy for customer *Needs to discussed.
| Booking Cancel: Recommended Professional (Professional details page & booking) |  | 14. User can cancel their booked services ? *When their booked service is accepted by the pro side. (Needs to discussed)
| Check booking status: Screen designed |  | 15. Payment Summary: Done
Notification page: Home Partial done
Profile: Change password
Log Out
Profile Edit & Update
Android Professional
Platform | Work Completed: 14/01/2020 | Android Professional: Work to be deliver 31/01/2020 | Android Professional: Pending Work/Discussion | Professional Pending Work
Android Professional | Splash Screen | 1. Profile: Update Bank Information: *API Pending----Done(not updating while updating bank information ) | 1. Rejected leads: *Reason for rejection (Screen/Dialog): Screen designed & implemented------Done *Functionality----Done in app, in admin panel it is pending | 1. Cancel leads Message/Reason: Message as a reason goes to User & Mein Haus admin Resource Name: Aayushi
| Walkthrough Screen | 2. Profile: Update business: *API Pending----Done | 2. Notification API for Professional & integration: *Pro side: User service cancel notification: Pending | 2. Cancellation Charge deduction (Service) & Cancellation timing : Pending
| Sign Up | 3. Profile: Update availability: *API Pending-----Done | 3. Profile: Update Document *API Pending----Done | 3. Registered professional verification by admin side: Resource Name: Aayushi
| Login | 4. Notification API for Professional & integration: *Pro side: Booking Leads notification: Done | 4. Profile: Rate: * Implemneted after Live application. | 4. Earnings Screen & two API's needed Resource Name: Aman & Aayushi
| Forget Password | 5. Payment gateway: Payment gateway: *PayPal---Integrated & done for testing purpose. *Card Number: 601100099130009 *Expiry Date: 12/2023 *CVV: 123 | 5. Profile: About Mein Haus: *Content pending *Contact Details needed by Client | 5. Customer ratings & reviews Screen & two API's needed Resource Name: Aman & Aayushi
| Prfessional Business Listing |  | 6. Payment gateway: *PayPal--Production level pending *We need client account details for verification. | 6. Profile: Rate: * Implemneted after Live application.
| Leads: List of booked services |  | 7. Professional Terms & Conditions: *Needed according to client | 7. Payment gateway: Production level pending *We need client account details for verification.
| Accept & Reject leads/booked services |  | 8. Profile: Help Center: *Content needed/pending *Contact details needed by client | 8. Assigning pros (on the basis of ratings): Our program once secured a sale, will ping the 3-5 highest rated individuals within an accepted radius that are available in the client specified time frame.
| Booking Details Page: Upcoming & Past bookings on the basis of booking status |  | 9. Professional side: Some Cases *Booked services, date slot, started service etc..Pending | 9. Professional side: Some Cases
| Start service: OTP |  | 10. Professional reject> User booked services: Past Bookings: *Cancelled services should must be coming in Past bookings: Needs to discussed.---But this is implemented for now. | 10. Professional payment(after completion of service) Admin side payment: 20% flat for every service goes to owner of the app after billing, other rest 80% payment paid to pro
| End service: OTP |  | 11. Accepted leads: Option to cancel services or leads by professional: *Needs to discussed-----Done & implemented
Profile: Change Password
Thank You Page
Log Out
Profile: Help Center page
Profile: About Mein house
Profile Edit & Update
iOS User
Platform | Work Completed: 14/01/2020 | iOS User: Work to be deliver 31/01/2020 | iOS User: Pending Work/Discussion
iOS User | Splash Screen | 1. Profile: Notification Toggle On/Off : *API Done *Functionality Done & implemented by developer side. | 1. Offers/Promotional cards: *API Done *Admin panel needed for this Offers/Promotional cards functionality to add different offers related to services. (Pending)
| Walkthrough Screen | 2. Whole functionality Notification Integration: * User side: Service book notification: Done *User side: Service accepted by professional: Done *User side: Service started by professional: Done *User side: Service ended by professional: Done *User side: Service start OTP (push notification): Done *User side: Service end OTP (push notification): Done | 2. Add Promo Code (Promotion): *API Done *Admin panel needed for this Add Promo Code functionality. (Pending) *Partial functionality is done by developer side.
| Sign Up |  | 3. Check booking status: *API Pending *Screen designed & implemented by developer side.
| Login |  | 4. Payment gateway: *PayPal *Pending
| Forget Password |  | 5. Whole functionality Notification Integration: *User side: Service rejected by professional (after accepting leads): Pending
| Home page: Different listed services, Services details, Search services, Popular services |  | 6. Profile: Offers tab functions: *Pending *Note: This point is related to point number 1.
| Services page: Different listed services, Search services, Services details |  | 7. Profile: About Mein Haus: *Content needed/pending *Contact Details needed by Client
| Service bookings |  | 8. Profile: Rate: * Implemneted after Live application.
| Booking Details Page: Upcoming & Past bookings on the basis of booking status |  | 9. User side: Some Cases: *bookings, services etc…Pending
| Add promo code: Partial done |  | 10. User Terms & Conditions *Needed according to client
| Choose Professional |  | 11. User Ratings (for professional): *API Needed *Screen needs to design *Notification needed (for users to rate professionals)
| Professional details |  | 12. Include services: *Civil work *Areawise and contract wise pricing will be done(per square foot) and for entering area, field is to be added at user side at the time of booking areawise services.
| Booking cancel |  | 13. Taking disclaimer and budgeting from customer: *Needs to discussed.
| Booking Cancel: Recommended Professional (Professional details page & booking) |  | 14. Agreement policy for customer *Needs to discussed.
| Check booking status: Screen designed |  | 15. User can cancel their booked services ? *When their booked service is accepted by the pro side. (Needs to discussed)
| Notification page: Home Partial done |  | 16. Payment Summary: API Needed
Profile: Change password
Log Out
Profile Edit & Update
iOS Professional
Platform | Work Completed: 14/01/2020 | iOS Professional: Work to be deliver 31/01/2020 | iOS Professional: Pending Work/Discussion
iOS Professional | Splash Screen | 1. Profile: Update Bank Information: *API Pending----Done | 1. Rejected leads: *Reason for rejection (Screen/Dialog): Not decided yet.
| Walkthrough Screen | 2. Profile: Update business: *API Pending----Done | 2. Notification API for Professional & integration: *Pro side: User service cancel notification: Pending
| Sign Up | 3. Profile: Update availability: *API Pending-----Done | 3. Profile: Update Document *API Pending----Done
| Login | 4. Notification API for Professional & integration: *Pro side: Booking Leads notification: Done | 4. Profile: Rate: * Implemneted after Live application.
| Forget Password |  | 5. Profile: About Mein Haus: *Content pending *Contact Details needed by Client
| Prfessional Business Listing |  | 6. Payment gateway: *PayPal--Integration at testing/ production level: Pending *We need client account details for verification.
| Leads: List of booked services |  | 7. Professional Terms & Conditions: *Needed according to client
| Accept & Reject leads/booked services |  | 8. Profile: Help Center: *Content needed/pending *Contact details needed by client
| Booking Details Page: Upcoming & Past bookings on the basis of booking status |  | 9. Professional side: Some Cases *Booked services, date slot, started service etc..Pending
| Start service: OTP |  | 10. Professional reject> User booked services: Past Bookings: *Cancelled services should must be coming in Past bookings: Needs to discussed.
| End service: OTP |  | 11. Accepted leads: Option to cancel services or leads by professional: *Needs to discussed
Profile: Change Password
Thank You Page
Log Out
Profile: Help Center page
Profile: About Mein house
Profile Edit & Update
Web User Platform
Platform | Work Completed | **Work Pending | Web: Work to be deliver 31/01/2020
Web | User Sign up | Home Page: Partial Done | 1. Professional: Update Document--Done
| User Login | Blog page: Functionality | 2. Professional: Update Bank Information---Done
| Service Listings and Service Details Page | About Us page: Functionality | 3. Professional: Update business----Done
| User Service Booking | Popular Services | 4. Professional: Update Availability----Done
| User Dashboard (Active Jobs) | Add promo code (Promotion) | 5. Professional: Accept & Reject leads----Done
| Home Page: Partial Done | Booking cancel: User & Pro | Web Pending Work
| User Logout | Check booking status | Booking cancel: User
| Blog page: Design | Notification page & integration | User & Pro: Notification page & integration
| About Us page: Design | User+Pro: Forget Password | Payment gatwey (User & Professional): PayPal--Integration at testing/ production level: Pending
| Contact us page: Design & functionality | User/Pro: Booking Details Page: Upcoming & Past bookings on the basis of booking status | Home Page: Partial Done
| Professional business listing (Signup/Login), Logout | Contact Us Page: Client contact us details required, Social media links required | Blog page & Help Center: Functionality
| Leads: List of booked services | Professional: Terms & Conditions: Needed according to client (For now page is designed with static data) | About Us page: Functionality
| Accept & Reject leads/booked services | Professional: Help Center: Content needed & contact details required by the client (For now page is designed with static data) | User: Booking Details Page: Upcoming & Past bookings on the basis of booking status
| Professional: Update Document | Professional: About MeinHaus: Content needed (For now page is designed with static data) | Area wise service functionality (User & Professional)
| Professional: Update Bank Information | Payment gatwey: PayPal--Integration at testing/ production level: Pending
| Professional: Update business | User/Pro: Profile Edit
10 Questions by team & their feedback response by client
Question No. | Questions | Feedback Response | Status (as per feedback response) | Out of Scope (tasks/functionalities) | Reasons
Q1 | Name of Payment Gateway which we need to implement in the app ? | Name of Payment Gateway -Preferably the most trusted/used platforms with generally the lowest fees - currently I'm using a program called Wave (may not be compatible from your location) however I think something like PayPal or Stripe would be recognizable enough. I would seek your input on this matter | payment would be done by stripe. Note: payment API will be used instead of payment gateway
Q2 | Name of the services which will be provided by the platform? | Name of Services which will be provided - all current items listed on jiffy platform will be included. We will also be adding in functions for New bathrooms, basement finishing, new kitchens, General Home Remodels, Architecture and engineering services. More into the spectrum of "General Contracting Services" Interior Design, Windows and Doors, Garage door maintenance, Landscaping. Drywall, Taping, Carpentry. | 1. include jiffy services 2. civil work also be included 3. areawise and contract wise pricing will be done(per square foot) 4. taking disclaimer and budgeting from customer 5. agreement policy for customer 6. booking will be confirmed by by pro.
Q3 | Categorisation will be there or not in Services ? If yes then on what basis and what would be the categories? | Categorization of Services - We are open to categorization, for now we will leave it uncategorized however we are exploring the option of Home maintenance and Home improvements as 2 separate categories. This will be a principal differentiator between us and competitive platforms like Jiffy on Demand. The purpose of our platform is to give home owners and general contractors access to all of the sub trades with out platform providing arbitration services to allow all users to access all of the local manpower with the click of a button. | need to discuss
Q4 | Some services does not depend on time like painting . It depends on Area so how the payment will be calculated for that ? | Pricing of Services - Many services can be chalked up to very basic pricing schemes, many of the new additions we are adding which Jiffy does NOT include will have much more complicated pricing calculators. On my end we are currently working on a set of algorithms that calculate prices based on a variety of factors. There is existing now technology on smartphones which measures the size of spaces using the camera feature, and this is something which we will likely want to incorporate into our program. We will also have a feature where clients can submit photos of the work area where our moderators on my end will view them and provide pricing through the app. It will appear on the customers end like the software has automatically generated this price, however we will continue to do it from the back end on more complex quotations. Ultimately we want to integrate a machine learning system where all quotes and purchases are logged into a database so our program can come up with its own pricing. The process of this will evolve in phases as our app gathers more clients, subscribers and funding. I will seek your feedback on how we can integrate some of these functions into our program. For all basic services we can copy pricing of Jiffy on demand and subtract 5% rounding to the nearest flat number. | we will consider it in next phase….. 1. we will consider the dispatch of pro based on the time of delivery.
Q5 | Can user cancel the service booking once it is started by the professional ? | Cancellaton of Service - There will be fees for cancelation which will escalate based on what phase of dispatch we are. For any basic cancellation (jobs under 200$) we can have a fee of say 25$. for larger sales, we will charge a percentage which is graded based on how close our tradesmen are to arriving at the project. If cancelled after tradesmen have been dispatched, we may charge say 25% of whatever the total sale was. For big jobs cancelled before mobilization, we will charge 5 or 10% | need to discuss once
/ | What would be the duration of booking to be accepted by professional ? We discussed it to be 5 min. ? But Please confirm it would be there or not ? If yes then the duration professional will get to accept it ? | Assigning pros - Our program once secured a sale, will ping the 3-5 highest rated individuals within an accepted radius that are available in the client specified time frame. It will specify to the professional the scope of work, location and predetermined price of service. the first of the users pinged that accept the job will get it. If the professional cancels and passes it onto the next guy AFTER accepting, there will be a small fee for doing so billed to his account. For now we will determine this to be equal to the amounts billed to clients for cancelling. | 1.push will be sent to the nearest available pros of 3-5* rating on FCFS basis
Q7 | If User is not providing otp to end the service so can Professional cancel the booking ?? | OTP - This is a good system to use for cancellation. needed only after user has already accepted the job and wishes to cancel. | can we put cancellation within 15 mins…penalty will be charged?(need to discuss)
Q8 | After accepting a booking, till what time professional can cancel the booking ? (If he has not started yet ) | Cancellation timing - This question will follow suit according to answer provided in section 6. | refer 6
Q9 | How we will approve the professional since there is no admin panel and we need to verify the docs first then allow the professional to be listed ?? | Admission of professionals - We will require basic information from each trades professional. This will include - Name and identity verification (government issued ID) including address, age. For plumbing and electrical we will require a license number. We will request from all trades a valid company insurance number and provider OR certificate. We will also require an business license or tax number. | approval needed from the user Note: admin panel will be made for basic approval.
Q10 | What would be the amount for professional to register his services on platform.? Will it be per type of service or constant amount ? Suppose if a professional register for multiple services and another for only one service so will the amount Vary ? | Pro Pricing - Professionals will be offered for the first year 35$ monthly or a discounted rate should they pay the full year at 250$. all pricing will be plus tax. For Ontario operations (this is where we will begin) will be 13% HST (harmonized sales tax). paid in monthly or annual instalments. likewise all customer purchases will also be taxed. | annual= 250$ monthly= $35 + 13% tax
|  | Professional Payout System - Professionals will be automatically paid 10% of their total fee for each project upon customer confirmation they have arrived and begun work. The clients end will be prompted with a push notification asking whether or not their professional has arrived and begun work. This will happen immediately after the initial deposit has been charged to the clients account. Upon reasonable completion, they will be paid an additional 60% of their fee, and the client will have say 24 hours to submit any requests for modifications before the pro will be paid out his remaining balance. | otp start= 10% end otp= 60% after inspection =30%
|  | Client pay structure - Upon booking we will put a hold on the requested amount of funds, not to be charged immediately. Once the professional has been dispatched we will charge 25% of the total. Upon confirmation of beginning we will charge 25% more. Upon reasonable completion we will bill 40%, and after inspection period final 10%. These numbers are being assigned with an open mindful discussion and alteration as necessary. | dispatch = 25% otp start = 25% otp end = 40% after completion = 10%
***Mein Haus QUERY RAISED 21/01/2020
Q11 | What will be the payment gateway according to canada for such a split payment? | Needs to discussion.
Q12 (Pro) | After registering as a pro | (Membership plan: For this add on functionality, screen needs to design) Anually - $250 monthly- $35 * for 1st service = $34.99 : $250 * for 2nd onwards = $19.99: $143
Q13 (Admin) | Billing amount for owner of the app | 20% flat for every service
1
Some additional issues for android User & Professional
1 | Android user> Home page search bar> Whole search bar should be clickable including search bar icon.-----Done
2 | Android User> Bookings> For new user/none booked services> in Upcoming page, there should be text as No upcoming booking available.-----Done
3 | Android User> Bookings page> Search functionality is pending.
4 | Android User> Home & Bookings page> Notification page heading name> In both of the page, the word should be Notifications, here s is missing------Done
5 | Android User + Professional> Profile> Profile image> for new users, image should be default. (Resource Name: Aayushi)
6 | Android User + Professional: Multiple login (Access token logout) (Resource Name: Aayushi)
7 | Android User> Booking Details page2 & Service Details page> 1. Remove the term "SERVICE PROVIDER"--------Done
8 | Android User> Booking Details page2> 2. For not available promocode, promocode is not applied but in booking details page, users entered promocode is displayed.------Done
9 | Android User> Booking Details page2> 3. Below applied promocode view, the line Promocode applied is missing (here, it is only represented sometime as "Pr/pro/promo etc").
10 | Android User> Booking Details page2> if user didn't apply any promocode, then from Booking details page, remove the promocode icon.------Done
11 | Android User> Booking Details page1> for the fields> Are there any timing constraints & What do you need?> Entered field should be multiline or should be scrollable while entering any data to these two fields.--------Done
12 | Android User> Booking Details page2> Edit icon> From booking details page, if user click on edit icon, then directly Address Details page2 should be open instead of Address Details page1.
13 | Android User> Edit Profile> Profile image change> from both option "Select photo from gallery & Capture photo from camera"> profille image is not updated-----Done
14 | Android Professional> Business Listing page> Chooose Your Services field> The view of this field should be in multiline or scrollable.-----Done
15 | Android Professional> Business Listing page> Full Business Address & Tell About Your Services> These two field should be in multiline or should be scrollable while entering data in to these fields.---pending
16 | Android Professional> Add Licence/Certification page> + Add Another Licence functionality is not working and Delete uploaded document functionality is not working.-----Delete document fun is done, +Add anothe licence is pending
17 | Android Professional> Thank You Page> From the contents, remove the word Erik Hall and here, client or support team contact number, email address is required (For now it is dummy).------Done
18 | Android Professional> Bookings> 1. Upcoming page, the line should be written as "No Upcoming Bookings Available" & 2. Past, the word Available is missing, here is should written as "No Past Bookings Available"----Done
19 | Android Professional> Leads page> "No Leads Available" texted line> Font colour/face> should be similar as bookings no upcoming & past bookings available.----Done
20 | Android Professional> Update Business page> Listed business uncheck and then scroll down or scroll up the screen> service are automatically autochecked.-----Done
21 | Android Professional> Edit Profile> While updating only full name or phone number or both full name, phone number, uploaded profile image is automatically removed.------Done
22 | Android Professional> Update Availability> For Open all days availability checkbox> if pro update their availability for open all days and goes back and again turn to this page, their selected checkbox "Open all days" gets change to "Enter Hours".------pending
23 | Android Professional> Leads > If user booked a single bookings, then in leads, here three leads are shown instead of one.-----Done
24 | Android Professional> Leads accepted > If professional accepted a single bookings, then in upcoming bookings, here three accepted bookings are shown instead of one.----Done
25 | Android Professional> Leads rejected > If professional rejected a single bookings, then in past bookings, here three rejected bookings are shown instead of one.----Done
26 | Android Professional> Update Document & Update Bank Information data populate problem (listed bank information is populated after logout)-----Pending
Some additional issues for iOS User & Professional
1 | iOS User> After signup from the Login page, if user goes back by back arrow, then on sign up page, Loader runs cotinuously and didn't stop.-----done
2 | iOS User> Home, Services & Bookings page> Notification page heading name> In both of the page, the word should be Notifications, here S is missing.
3 | iOS User> Search bar> font colour, design, text & search bar icon> on Home page & Bookings page> dissimilar to android.
4 | iOS User> Popular services> Listings View> not similar to the android.----
5 | iOS User> Services page> tab layout design for different categorized services and their name> dissimilar to android.
6 | iOS User> Bottom tab> Service> The word should be Services, here s is missing.
7 | iOS User> Services page> Search functionality> except first tab of services i.e All Services, search functionality is not working for other categorized services.
8 | iOS User> Bookings page> UPCOMING & PAST> letter cases> In android it is in lowercase while in iOS it is in uppercase (dissimilar to android).
19 | iOS pro> business listing> choose your services>on opening of "choose your services" arrow is not clickable and update business is opening, while selecting no. of services and clicking on save then again click on choose ur services>selected services are disapeared
20 | iOS pro> edit profile> phone number> can't edit,because we cannot cut and add numbers in this field
21 | iOS pro> update bank information > our plan> when going back to bank information, bank info doesn't update and alert is comming after payment "services updated successfully"
22

## Validations
S.No. | Fields | Descriptions
1 | EIN Number (Employer Identification Number) | The EIN is nine digits long, and the format is XX-XXXXXXX. For example: 12-3456789
2 | SSN (Social Security Number ) | SSN consists of nine digits number, commonly written as three fields separated by hyphens: AAA-GG-SSSS. The first three-digit field is called the "area number". The central, two-digit field is called the "group number". The final, four-digit field is called the "serial number". For example: 111-22-3333
3 | Routing Number | Routing Number consists of nine digits number. For example: 123456789
4 | Account Number | Routing Number consists of eight digits number. For example: 12345678
5 | Profile Image | The upload function should accept images format only, ex:jpg,png,gif
6 | Profile Image | The upload function should not accept file size more than 500KB
7 | Date of birth | The date should accept 18+ years old
8 | Password Field | The minimum length of the password should be eight characters and should contain uppercase/lowercase letters, numbers, and special charaters. The maximun length of a password should be 20 character.

## Admin features
S.NO | Mein Haus Admin Pending Work
1 | Booking management: Booking details, User details, Professional details, Service charge, Cancel booking button, Complete booking button, Payment status change & refund.----P
2 | Static content management------P
3 | Transaction management--------P
4 | Blog Management----------P
5 | Help Center Management--------P
6 | Offers/Promotional cards functionality to add different offers related to services.
7 | Professional management: Professional business listings view, Verification, Block/Unblock
8 | Users management: User details view, Block/Unblock
9 | Service management: List view, Add/Edit service, View service details, Delete Service
10 | Contact Us
11 | Admin Edit profile
12 | Admin Change password
13 | Admin Logout